## POC CI Project Plan
Phase | Task | Sub-task | Detail | Req # | Workstream Activities | Owner | Duration (days) | Start Date | Baseline End Date | Revised End Date | Dependencies | Comments
Planning | 1 | #REF! | #REF! |  | CI Use Cases
Planning | 1 | #REF! | #REF! |  | Define business use cases | <Customer>
Planning | 1 | #REF! | #REF! |  | Define KPIs supporting use cases | <Customer>
Planning | 1 | #REF! | #REF! |  | Define audience/personas | <Customer>
Milestone | 1 | #REF! | #REF! |  | Documented success criteria and use cases | <Customer>
Planning | 3 | 0 | 4 |  | Security Requirements
Planning | 3 | 1 | 0 |  | Review encryption requirements | <Customer>/Partner
Planning | 3 | 0 | 4 |  | Identify accounts for data sources | <Customer>
Setup | 4 | #REF! | #REF! |  | Environments
Setup | 4 | 1 | #REF! | #REF! | Provision CI environment | <Customer>/Partner/MS |  |  |  |  | 1.1.1
Setup | 4 | 2 | 0 |  | Grant Environment Access | <Customer>
Design | 5 | 0 | 0 | 5.0.0 | CI design
Design | 5 | 0 | 1 | 5.0.1 | Design unified customer profile | Partner
Design | 5 | 0 | 2 | 5.0.2 | Design activities | Partner
Design | 5 | 0 | 3 | 5.0.3 | Design measures/KPIs | Partner
Milestone | 5 | 1 | 0 |  | CI data requirements defined & documented | <Customer>/Partner/MS
Design | 6 | 0 | 4 | 6.0.4 | CI data sources
Design | 6 | 1 | 0 | 6.1.0 | Identify <Customer> source systems and data access methods | <Customer> |  |  |  |  | 2.1.1
Design | 6 | 1 | 1 | 6.1.1 | Design entities | Partner |  |  |  |  | 2.1.1, 2.1.2
Design | 6 | 1 | 2 | 6.1.2 | Design relationships | Partner |  |  |  |  | 2.1.1, 2.1.2, 2.1.3
Design | 6 | 1 | 3 | 6.1.3 | Design map/match/merge rules for unified profile | Partner |  |  |  |  | 2.1.1, 2.1.2
Milestone | 6 | 2 | 0 |  | Entity Relationship Diagram, Data Flow Diagram, M3 logic complete | <Customer>/Partner
Design | 7 | 3 | 0 | 7.3.0 | Outbound integrations
Design | 7 | 3 | 1 | 7.3.1 | Design segments | Partner |  |  |  |  | 2.1.0
Design | 7 | 3 | 2 | 7.3.2 | Design export destinations | Partner
Milestone | 7 | #REF! | #REF! |  | Downstream systems and use cases documented | <Customer>/Partner
Build | 8 | 0 | #REF! |  | Data Prep
Build | 8 | 1 | 0 |  | Identify data quality | Partner
Build | 8 | 2 | 0 |  | Identity data cleansing strategy | Partner
Build | 8 | 2 | 0 |  | Execute data cleansing strategy | Partner
Build | 8 | 3 | 0 |  | Validate data cleansing | Partner
Milestone | 8 | 3 | 0 |  | Data cleansing testing passes | <Customer>/Partner
Build | 9 | 0 | #REF! | #REF! | Data ingestion
Build | 9 | 0 | #REF! | #REF! | Define data sources | Partner |  |  |  |  | 2.1.0
Build | 9 | 0 | #REF! | #REF! | Define entities | Partner |  |  |  |  | 2.1.2
Build | 9 | 0 | #REF! | #REF! | Define relationships | Partner |  |  |  |  | 2.1.3
Build | 9 | 0 | #REF! | #REF! | Execute data ingestion run (<1m records) | Partner |  |  |  |  | 3.0.2, 3.0.3
Build | 9 | 1 | 0 |  | Validate data ingestion | Partner
Milestone | 9 | 0 | #REF! | #REF! | Data successfully ingested | <Customer>/Partner |  |  |  |  | 3.0.2, 3.0.3
Build | 10 | 0 | #REF! | #REF! | Unified profile
Build | 10 | 1 | 0 | 10.1.0 | Define map/match/merge rules | Partner |  |  |  |  | 3.0.4
Build | 10 | 0 | #REF! |  | (Optional) Apply self-conflation | Partner
Build | 10 | 1 | 1 | 10.1.1 | Execute M3 | Partner |  |  |  |  | 3.1.1
Build | 10 | 2 | 0 |  | Validate Customer Entity successfully created | Partner
Milestone | 10 | 2 | 0 |  | Customer Entity validation successful | <Customer>/Partner
Build | 11 | 0 | 0 | 11.0.0 | Activities and measures/KPIs
Build | 11 | 2 | 0 | 11.2.0 | Define activities | Partner |  |  |  |  | 2.1.2
Build | 11 | 2 | 1 | 11.2.1 | Define measures/KPIs | Partner |  |  |  |  | 2.1.3
Build | 11 | 2 | 2 | 11.2.2 | Execute activites and measures/KPIs | Partner |  |  |  |  | 3.1.2,3.2.1,3.2.2
Build | 11 | 3 | 0 |  | Validate activities and measures | Partner
Milestone | 11 | 4 | 0 |  | Activities and measures/KPIs validation successful | <Customer>/Partner
Build | 12 | 0 | 0 | 12.0.0 | Outbound integrations/Activate
Build | 12 | 3 | 0 | 12.3.0 | Define segments | Partner |  |  |  |  | 2.3.1
Build | 12 | 3 | 1 | 12.3.1 | Define export destinations | Partner |  |  |  |  | 2.3.2
Build | 12 | 3 | 2 | 12.3.2 | Execute segment creation and export | Partner |  |  |  |  | 3.2.3, 3.3.1, 3.3.3
Build | 12 | 3 | 3 | 12.3.3 | Validate segment(s) export | Partner |  |  |  |  | 3.2.3, 3.3.1, 3.3.3
Milestone | 11 | 0 | 0 |  | Segments created and successfully exported | <Customer>/Partner

## CI Project Plan
Phase | Task | Workstream Activities | Owner | Customer Involved Teams | Duration (days)
Planning | 1 | CI Use Cases | Customer/Partner | Analysts, Business SMEs
Planning | 1.1 | Define business/technical use cases | Customer/Partner | Analysts, Business SMEs
Planning | 1.2 | Define rules/logic for the customer definition | Customer/Partner | Analysts, Business SMEs
Planning | 1.3 | Define KPIs supporting use cases | Customer/Partner | Analysts, Business SMEs
Planning | 1.4 | Define segments supporting use cases | Customer/Partner | Analysts, Business SMEs
Planning | 1.5 | Define audience/personas | Customer/Partner | Analysts, Business SMEs
Planning | 1.6 | Define activation scenarios | Customer/Partner | Analysts, Business SMEs
Planning | 1.7 | Define export destinations | Customer/Partner | Analysts, Business SMEs
Milestone | 1.7 | Documented success criteria and use cases | Customer/Partner
Planning | 2 | Application Lifecycle Management
Planning | 2.1 | Identify CI Approach (BYODL, Managed DL) | Customer/Partner/MS | Architect, Security, Infrastructure
Planning | 2.2 | Plan CI environments (Dev, Test, UAT, Production) | Customer/Partner/MS | Architect, Security, Infrastructure
Planning | 2.3 | Document agreed upon SDLC/ALM | Customer/Partner | IT, Project Delivery
Planning | 2.4 | Define sample (<100K), QA (<3m), and full data ingestion schedule/approach | Customer/Partner | IT, Project Delivery
Planning | 2.5 | Develop go-live release plan and schedule | Customer/Partner | IT, Project Delivery
Milestone | 2.6 | ALM/SDLC documented | Customer/Partner/MS
Planning | 3 | Architecture & Security
Planning | 3.1 | Define & document holistic architecture | Customer/Partner | Architect, Security/Privacy, Infrastructure, IT
Planning | 3.3 | Review encryption requirements | Partner/MS | Architect, Security/Privacy, Infrastructure, IT
Planning | 3.4 | Identify system accounts for data sources | Customer/Partner | Security/Privacy, Infrastructure
Planning | 3.5 | Identify data flow security requirements | Partner | Architect,Security/Privacy, Infrastructure
Planning | 3.6 | Identify and document data privacy and compliance requirements | Partner | Security/Privacy/Legal, Infrastructure
Milestone | 3.7 | Architecture, Security & Compliance review & sign off | Customer
SteerCo | 3.8 | Steering Committee Review and Sign off for Planning Phase | Customer/Partner/MS
Setup | 4 | Environments
Setup | 4.1 | Provision CI environments | Customer/Partner/MS | Infrastructure, IT
Setup | 4.2 | Grant Environment Access | Customer | Infrastructure, IT
Milestone | 4.3 | Environments provisioned with access | Customer/Partner
Define | 5 | CI data sources
Define | 5.1 | Identify Customer source systems and data access methods | Customer/Partner | Data Analysts, Infrastructure
Define | 5.2 | Design entities | Partner
Define | 5.3 | Design relationships | Partner
Define | 5.5 | Document Entity Relationship Diagram (ERD) | Partner
Define | 5.4 | Design and document map/match/merge rules for unified profile | Partner
Define | 5.5 | Sample & QA data criteria defined | Customer/Partner | Analysts
Milestone | 5.6 | ERD, M3 logic finalized | Customer/Partner | Architect/Analysts
SteerCo | 5.6 | Steering Committee Review and Sign off | Customer/Partner/MS
Prep | 6 | Data & M3 Prep
Prep | 6.1 | Define & document data flow | Customer/Partner | Architect, Security/Privacy, Infrastructure, IT
Prep | 6.2 | Identify data quality | Customer/Partner | Analysts
Prep | 6.3 | Identity data cleansing strategy | Customer/Partner | Architect/Analysts
Prep | 6.4 | Execute data cleansing strategy | Partner
Prep | 6.5 | Validate data cleansing | Customer/Partner | Analysts
Prep | 6.6 | Validate sample & QA criteria (for BYODL) | Customer/Partner | Analysts
Prep | 6.7 | M3 Rules Confirmed | Partner
Milestone | 6.6 | Data Validated | Customer/Partner | Analysts
Customer Insight Design/Build/Test (Iterate)
Design | 7 | Customer Insights Design (Iterate)
Design | 7.1 | Design unified customer profile | Partner
Design | 7.2 | Design activities | Partner
Design | 7.3 | Design measures | Partner
Design | 7.4 | Design segments | Partner
Design | 7.5 | Design activities | Partner
Design | 7.6 | Design export destinations | Partner
Design | 7.7 | Define enrichments | Customer
Build | 8 | Data
Build | 8.1 | Ingestion (Subset) | Partner
Build | 8.2 | Define entities | Partner
Build | 8.3 | Define relationships | Partner
Build | 8.4 | Unified profile
Build | 8.5 | Configure map/match/merge rules | Partner
Build | 8.6 | (Optional) Apply self-conflation | Partner
Build | 8.7 | Execute M3 | Partner
Build | 8.8 | Activities, measures/KPIs, Segments, Outbound
Build | 8.9 | Configure activities | Partner
Build | 8.1A | Configure measures/KPIs | Partner
Build | 8.2A | Configure segments | Partner
Build | 8.3A | Configure export destinations | Partner
Build | 8.1A | Execute activites and measures/KPIs | Partner
Build | 8.2A | Execute segment creation and export | Partner
Test | 9 | System Testing | Partner
Test | 9.1 | Validate data ingestion | Partner
Test | 9.2 | Validate Customer Entity successfully created | Partner
Test | 9.3 | Validated M3 Rules | Partner
Test | 9.4 | Validate activities and measures | Partner
Test | 9.5 | Validate segment(s) export | Partner
Test | 9.6 | Validate export destinations | Partner
Milestone | 9.7 | Customer Insights Configuration Complete (Subset Data) | Customer/Partner | Analysts, Business SMEs
SteerCo | 9.6 | Steering Committee Review and Sign off | Customer/Partner/MS
UAT | 10 | Execute
UAT | 10.1 | Run ingestion, M3, Measures, and Segments for Full Data Load | Partner
UAT | 10.2 | Execute user acceptance testing critiera | Customer/Partner | Analysts, Business SMEs
UAT | 10.3 | Remediate
UAT | 10.4 | Implement remediations | Customer/Partner | Analysts, Business SMEs
UAT | 10.5 | Deploy remediations | Customer/Partner | Analysts, Business SMEs
UAT | 10.6 | Validate remediations | Customer/Partner | Analysts, Business SMEs
Milestone | 10.7 | UAT Sign Off | Customer/Partner | Analysts, Business SMEs
SteerCo | 10.8 | Steering Committee Review and Sign off | Customer/Partner/MS |  | April 30th
Deploy | 11 | Execute
Deploy | 11.1 | Deploy configurations to production | Customer/Partner | Architect, Infrastructure, IT
Deploy | 11.2 | Execute go-live plan for data ingestion, M3, Measures and Segments | Customer/Partner | Architect, Infrastructure, IT
Deploy | 11.3 | Conduct post-deployment smoke testing | Customer/Partner | Analysts, Business SMEs
Milestone | 11.4 | Smoke testing validated; customer signs off | Customer/Partner
Hypercare | 12 | Support & Knowledge Transfer
Hypercare | 12.1 | Post production go-live support | Customer/Partner | Analysts, Business SMEs, IT
Hypercare | 12.2 | IT hand off | Customer/Partner | Analysts, Architect, IT
Hypercare | 12.3 | Business sponsorship | Customer/Partner | Analysts, Business SMEs
Hypercare | 12.4 | Train the trainer | Customer/Partner | Analysts, Business SMEs
Adoption | 13 | Business Adoption and Validation
Adoption | 13.1 | Validate Use Cases Success | Customer | Analysts, Business SMEs
Adoption | 13.2 | Train business champions | Customer | Analysts, Business SMEs
Adoption | 13.3 | Evaluate ROI using Segments | Customer | Analysts, Business SMEs
Adoption | 13.4 | Ongoing: CI Effectiveness and Feedback loop | Customer/MS | Analysts, Business SMEs
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!